## Slide 1
FPGA-BASED SYSTEM DESIGN · PROJECT REVIEW 2
SHA-256 Accelerator
Progress Review
RTL and verification complete · integration measured · synthesis next
44 RTL verification checks passing · 0 failures · both configurations
PRESENTED BY
Amritha S · 23BEC1368
TARGET DEVICE
ZedBoard · XC7Z020-1CLG484C
TOOLCHAIN
Vivado 2022.2 · Vitis 2022.2
STATUS
Week 8 of 12
Notes: Review 2 is a progress review. Lead with what is measured, be explicit about what is not yet measured, and present the new finding on slide 6.

## Slide 2
Where the Project Stands
01
Green is measured, amber is running, red is not started
44
RTL checks passing
ZERO FAILURES
100%
of planned RTL written
AND VERIFIED
2 / 2
configurations working
BOTH IN SIMULATION
0
hardware measurements
SYNTHESIS IS NEXT
Deliverable | Status | Evidence
Python golden model | DONE | 5 NIST vectors incl. 1M chars; cross-checked against hashlib
Compression core, Config A | DONE | 66 cycles/block confirmed in simulation
Compression core, Config B | DONE | 34 cycles/block confirmed in simulation
AXI4-Lite register file | DONE | Register map verified by BFM read/write
AXI4-Stream wrapper | DONE | Back-pressure and multi-block chaining verified
Top-level IP | DONE | 9/9 system checks, both configurations
Per-round trace verification | DONE | a..h and W[t] match golden model at all 64 rounds
Soak test | DONE | 12 messages incl. 55/56/63/64/65-byte padding boundaries
Software SHA-256 + padding | DONE | Compiled and verified natively against NIST
Vitis driver and application | DONE | Written; compiles against the BSP
Vivado build automation | IN PROGRESS | Script written; first run in progress
Synthesis, area and Fmax | PENDING | Blocked on the build above
Board bring-up and measurement | PENDING | Scheduled Week 9
Review 2 · Amritha S · 23BEC1368 · 1

## Slide 3
Recap — The Question This Project Answers
02
Unchanged since Review 1
SHA-256 rounds are strictly data-dependent: round t+1 consumes round t.
Two unrolled rounds cannot be separated by a register without losing the cycle saving,
so the adder chains stack in series and maximum frequency must fall.
Config A — iterative
1 round per cycle
66 cycles per 512-bit block
one 5-input adder chain
Config B — 2× unrolled
2 rounds per cycle
34 cycles per 512-bit block
TWO adder chains in series
Unrolling is a net win only if Fmax(B) / Fmax(A) > 34 / 66 = 0.515
Threshold declared at Review 1, before any synthesis was run. That has not changed — but Review 2 has refined it. See slide 06.
Review 2 · Amritha S · 23BEC1368 · 2

## Slide 4
Verification Evidence
03
44 checks, run by a single command, zero failures
Suite | Checks | What it proves | Result
Core RTL (tb_sha256.v) | 21 | Sigma/sigma/Ch/Maj against the model; K ROM entries; NIST digests for both configs; A vs B identical; 66 and 34 cycle counts | PASS
System AXI, Config A (tb_sha256_top.v) | 9 | Register map; single-block, empty and two-block messages driven entirely through AXI4-Lite and AXI4-Stream; re-arm; soft reset | PASS
System AXI, Config B | 9 | The same nine checks against the unrolled core | PASS
Trace and soak (tb_sha256_soak.v) | 5 | Working variables a..h AND the message schedule W[t] compared at all 64 rounds; 12 messages across padding boundaries | PASS
Software reference (native gcc) | 10 | 5 NIST vectors including one million characters; padding lengths; byte-swap involution | PASS
Reproducible in one command: make all — regenerates the golden vectors, then runs every suite above in about ninety seconds.
Review 2 · Amritha S · 23BEC1368 · 3

## Slide 5
New Since Review 1 — Per-Round Verification
04
Closing the gap flagged as outstanding at Review 1
Hash bugs — a wrong Sigma constant, a schedule off-by-one, a missing final accumulation — all produce output that still looks like a valid digest. End-to-end testing cannot localise them.
1
Golden model emits the trace
The Python reference writes the working variables a..h and the schedule word W[t] at the top of every one of the 64 rounds
2
Testbench reads it with $readmemh
trace_vars.mem holds 64 × 256-bit snapshots; trace_w.mem holds 64 schedule words
3
Sampled against the core's own round counter
Keying on u_A.t removes any need to guess the load-phase latency, and driving on the negative edge avoids racing the DUT's own clocked block
4
Compared every round, not just at the digest
A mismatch reports the exact round number, the value obtained and the value expected
Result: working variables a..h and the message schedule W[t] both match the golden model at ALL 64 ROUNDS. Verification is now exact at every level of the hierarchy, not merely end to end.
Review 2 · Amritha S · 23BEC1368 · 4

## Slide 6
New Finding — The Threshold Moved
05
Integration measurement changed the break-even condition
Review 1 derived the break-even from the CORE cycle counts alone. Measuring the integrated system revealed a fixed streaming overhead that Review 1 did not account for.
 | Config A | Config B | Saving | Break-even ratio
Compression only | 66 cycles | 34 cycles | 32 cycles | 34/66 = 0.515
Measured at system level | 85 cycles | 53 cycles | 32 cycles | 53/85 = 0.624
Fixed streaming overhead | 19 cycles | 19 cycles | 0 | — identical in both
Where the 19 cycles go
Sixteen AXI4-Stream beats to deliver one 512-bit block, plus the submit and hash-update handshake. Identical for both configurations, because it is outside the compression loop.
Why the threshold rose
A fixed overhead dilutes a proportional saving. The 32-cycle gain is unchanged, but it is now 32 of 85 rather than 32 of 66 — so Config B must retain MORE frequency to break even.
REVISED CRITERION Fmax(B) / Fmax(A) > 0.624 — unrolling now has a harder bar to clear
Review 2 · Amritha S · 23BEC1368 · 5
Notes: This is the slide to spend time on. It is a genuine finding that emerged from doing the integration work rather than from the original analysis, and it makes the Review 1 prediction more demanding rather than less.

## Slide 7
System Integration — Verified Over Real AXI
06
The testbench drives the design exactly as the processor will
1
AXI4-Lite write
BLOCK_CNT = number of 512-bit blocks
2
AXI4-Lite write
CTRL = START | INIT
3
AXI4-Stream
16 beats of 32 bits per block, with back-pressure between blocks
4
AXI4-Lite poll
STATUS until DIGEST_VALID asserts
5
AXI4-Lite read
eight register reads return H0..H7
Verified over AXI
Register map and VERSION ID
Single-block message
Empty message
Two-block message, chaining
Re-arm without reset
Soft reset then hash again
Back-pressure between blocks
Digest readback, 8 registers
Two integration bugs found and fixed — both in the testbench, not the RTL
1. The AXI bus functional model deasserted VALID as soon as READY appeared. A transfer completes on the rising edge where both are high, so VALID must be held THROUGH that edge — dropping it early loses the transfer silently.
2. Driving stimulus on the positive edge races the design's own clocked block, letting the core latch block_valid a cycle early and shifting the entire round trace by one. All stimulus now drives on the negative edge.
Review 2 · Amritha S · 23BEC1368 · 6

## Slide 8
In Progress — Synthesis and Implementation
07
Fully scripted so both configurations see an identical system
vivado -mode batch -source vivado/build_system.tcl # Config A
vivado -mode batch -source vivado/build_system.tcl -tclargs 1 # Config B
1
Package sha256_top as a Vivado IP
CORE_SELECT exposed as a parameter
2
Build the block design
ZYNQ7 PS + AXI DMA (MM2S only) + accelerator
3
Apply an identical timing constraint
same 10 ns target for both configurations
4
Synthesise, implement, generate bitstream
unattended, roughly 15 minutes each
5
Extract accelerator-only resource counts
filters out the DMA and interconnect
6
Export the XSA for Vitis
hardware handoff for the software build
Why the build is scripted rather than clicked
The whole project rests on comparing two frequency numbers. If the two builds differ in interconnect topology, constraint wording or implementation strategy, the comparison is worthless. Scripting guarantees the surrounding system is bit-for-bit identical and only CORE_SELECT changes — which is what makes this a controlled experiment rather than two unrelated designs.
Review 2 · Amritha S · 23BEC1368 · 7

## Slide 9
Results Table — Ready to Fill
08
Every measurement has a defined source; nothing is estimated
Metric | Config A | Config B | Source | Status
Cycles per 512-bit block (core) | 66 | 34 | simulation | MEASURED
Cycles per block (system) | 85 | 53 | simulation | MEASURED
Streaming overhead | 19 | 19 | derived | MEASURED
Fmax (MHz) | ____ | ____ | reports/summary.txt | pending
Fmax ratio B/A | — | ____ | derived | pending
vs revised threshold 0.624 | — | ____ | derived | THE RESULT
Accelerator LUT | ____ | ____ | reports/summary.txt | pending
Accelerator FF | ____ | ____ | reports/summary.txt | pending
BRAM | ____ | ____ | reports/summary.txt | expect 0
DSP48 | ____ | ____ | reports/summary.txt | MUST be 0
Throughput on board (Mbit/s) | ____ | ____ | UART, TEST 3 | pending
Software throughput (Mbit/s) | ____ | ____ | UART, TEST 3 | pending
Speedup over software | ____ | ____ | derived | expect ~3x
Three rows are already measured in simulation and will not change. The rest come from two Vivado reports and one UART session. Once those exist, the results chapter is arithmetic.
Review 2 · Amritha S · 23BEC1368 · 8

## Slide 10
Remaining Work to Review 3
09
Four weeks, with two designated buffer weeks already spent
8
Run both Vivado builds; record area and Fmax
reports/summary.txt exists for A and B
critical path
9
Vitis workspace; board bring-up; NIST conformance on hardware
TEST 1 and TEST 2 pass on the board
critical path
10
Benchmark hardware vs software; compute the Fmax ratio
Results table complete
has slack
11
Capture waveforms; draft the report
Five waveforms captured, draft complete
has slack
12
Slides, demo rehearsal, final submission
All deliverables submitted
has slack
Weeks 8 and 9 are the only ones on the critical path. Everything after them is analysis and writing, both of which can absorb delay. If board access slips, the fallback is to report synthesis results only and present the hardware demo at Review 3.
Review 2 · Amritha S · 23BEC1368 · 9

## Slide 11
Risk Register — Updated
10
Four of the seven Review 1 risks are now retired
R1
Big-endian word ordering
RETIRED
Verified over AXI with real streamed beats; per-round trace confirms W[t] at every round
R2
Schedule window off-by-one
RETIRED
W[t] compared against the golden model at all 64 rounds
R3
Missing final H accumulation
RETIRED
NIST digests correct for 12 messages, both configurations
R4
Chaining across blocks
RETIRED
Two- and three-block messages verified end to end
R5
Config B fails timing badly
OPEN
Expected. This is the result, not a failure — the revised 0.624 threshold makes it more likely
R6
Cache coherency on the board
OPEN
Not yet exercised. Xil_DCacheFlushRange is in the driver; documented as the first thing to check
R7
Board access in Weeks 8-9
OPEN
Only remaining schedule risk. Fallback is synthesis-only results at Review 3
The retired risks were retired by evidence, not by assertion — each one names the test that closed it.
Review 2 · Amritha S · 23BEC1368 · 10

## Slide 12
Where we are
Design and verification are complete and reproducible. Integration measurement has already sharpened the research question. What remains is two synthesis runs, one board session, and arithmetic.
Board access
ZedBoard for Weeks 8-9
Confirmation
Is the revised 0.624 threshold accepted?
Review 3 scope
Full results, or results plus live demo?
Thank you — questions welcome
Amritha S · 23BEC1368 · amritha.s2023@vitstudent.ac.in